# 2026 PROGRAM PLAN

Scalable Sales Enablement and Demand Generation

Planning Period: January 1 – December 31, 2026  |  Version: Draft

# Program Overview

This program encompasses two integrated workstreams: (1) Mature and align advanced sales enablement support to an optimized go-to-market strategy, and (2) Build and align a revamped marketing demand-gen strategy and execution. Success requires tight coordination between Marketing, Sales, BDRs, CX, and Strategic Insights teams.

# 2026 Program Priorities

- Repeatable sales motions with predictable pipeline forecasting

- Data-driven prioritization of seller and BDR activity (beyond quantity targets)

- Cross-functional orchestration with systematic feedback loops (M/S/B/C)

- Content infrastructure tied to usage tracking and win correlation

- Insight-to-action-to-insight mechanisms operating consistently

# Q1: Foundation & Infrastructure

Quarter Focus: Implement recommended changes from AUX insights, establish tool infrastructure, and build diagnostic capabilities for ongoing measurement.

| Deliverable | Owner | Supported By | Target |
| --- | --- | --- | --- |
| Vet and implement marketing automation tool (vetting Dec-Jan, live by end of Q1) | Kelley Moore | AUX, Marketing, Product | Mar 31 |
| Implement lead tracking processes with activity-level analytics | Kelley Moore | AUX, Business Systems, Sales, BDRs | Mar 31 |
| Finalize and implement sales tools (Gong, comp tools) as standard across org | Kelley Moore | Sales, Product, Technology | Feb 28 |
| Update website home page per AUX recommendations | Kelley Moore | AUX, Trapp, Design | Mar 31 |
| Establish baseline diagnostic infrastructure: conversion analytics, productivity metrics, data accuracy reporting | Kelley Moore | Business Systems, Data Team | Mar 31 |
| Define and document LTV/CAC tie-ins for all programs | Kelley Moore | Finance, Strategic Insights | Mar 31 |

Key Metrics: Marketing automation operational, sales tools adopted org-wide, baseline activity-to-output analytics in place, lead tracking reporting functional.

# Q2: Content Infrastructure & Enablement Foundation

Quarter Focus: Build searchable content library with usage tracking, establish cross-team feedback loops, and implement win/loss intelligence program.

| Deliverable | Owner | Supported By | Target |
| --- | --- | --- | --- |
| Complete sales and BDR collateral audit; create/update assets with UPSTACK branding | Kelley Moore | Sales, Marketing, 3rd party branding | May 31 |
| Deploy content library in Enablement Hub: searchable, tagged by stage, with version control and ownership | Kelley Moore | Business Systems | Jun 30 |
| Implement content usage tracking with win correlation analytics | Kelley Moore | Data Team, Business Systems | Jun 30 |
| Launch structured win/loss program with conversion intelligence | Kelley Moore | Sales, CX, Strategic Insights | May 31 |
| Run 4-month campaign reporting; extract performance insights | Kelley Moore | Data Team | Jun 30 |
| Establish systematic cross-team feedback loops (Marketing/Sales/BDRs/CX) | Kelley Moore | All GTM teams | Jun 30 |
| Document and distribute ICPs (from AUX) with usage guidance for Sales/BDRs | Kelley Moore | AUX | May 31 |

Key Metrics: Content library live with 100% of priority assets, usage tracking operational, win/loss data feeding back into enablement, cross-team handoff protocols documented and in use.

# Q3: Playbooks, Repeatability & Experimentation Framework

Quarter Focus: Convert learnings into field-ready playbooks, establish testing cadence, and prove repeatability of winning motions.

| Deliverable | Owner | Supported By | Target |
| --- | --- | --- | --- |
| Develop playbooks by vertical/supplier category/buying scenario with talk tracks, objection handling, proof points, SME triggers | Kelley Moore | Sales, CX, SME group | Sep 30 |
| Structure buyer journey by stage; align specific content to need at each stage | Kelley Moore | Sales, Marketing, CX | Aug 31 |
| Create customer win stories and case write-ups mapped to GTM priorities | Kelley Moore | Sales, CX, SME group | Sep 30 |
| Establish experimentation/testing framework with decision criteria: 'if we find X, we do Y' | Kelley Moore | Strategic Insights, Sales | Aug 31 |
| Harvest and repurpose insights from TSD events into UPSTACK-branded assets | Kelley Moore | Supplier Relations (Ad Ops) | Ongoing |
| Implement structured onboarding audit with ramp time benchmarks | Kelley Moore | HR, Sales Leadership | Sep 30 |
| Coordinate proposal/quote/audit automation with portal and AI system capabilities | Kelley Moore | Product, Technology | Sep 30 |

Key Metrics: Playbooks deployed and tracked for adoption, ramp time baseline established, testing framework producing actionable insights, buyer journey content mapping complete.

# Q4: Scale, Optimize & Prove Predictability

Quarter Focus: Validate repeatability and predictability of sales motions, optimize based on full-year learnings, prepare 2027 roadmap.

| Deliverable | Owner | Supported By | Target |
| --- | --- | --- | --- |
| Validate same motions producing consistent results across teams (repeatability proof) | Kelley Moore | Sales, BDRs, Strategic Insights | Nov 30 |
| Document known ramp time with accurate pipeline forecasting methodology | Kelley Moore | Sales Leadership, Finance | Dec 15 |
| Complete structured log of insights-driven tests, decisions, actions, and results | Kelley Moore | Strategic Insights | Dec 31 |
| Finalize 2027 capacity planning with budget allocation to highest-performing channels/activities | Kelley Moore | Finance, Sales Leadership | Dec 15 |
| Establish centralized intake for customer engagement inputs (CAB, interviews, CX conversations) | Kelley Moore | Marketing, CX, Product | Nov 30 |
| Deliver EOY analysis: WHY we hit or didn't hit each target, with distribution plan for findings | Kelley Moore | Strategic Insights, Sales Leadership | Dec 31 |

Key Metrics: Demonstrated repeatability across teams, accurate forecasting within 10% variance, full test log with actionable 2027 recommendations, capacity model validated.

# What Success Looks Like

By December 31, 2026, this program will have achieved:

## Infrastructure & Tools

- New comp plan tool operational

- Marketing automation platform generating and tracking demand

- Revenue intelligence (Gong) embedded in daily workflows

- Cross-team source-of-truth per account (Lumopath/Gong/SFDC/Insights integrated)

## Content & Enablement

- Searchable content library by stage with usage tracking and win correlation

- Playbooks and templates used consistently, tracked for testing/analysis

- Systematic case study creation practice producing assets aligned to GTM priorities

- Structured onboarding reducing time-to-impact for new hires

## Process & Intelligence

- Analytics showing what input produces what output, at the activity level

- Insight-to-action-to-insight mechanisms operating continuously

- Data-driven prioritization of seller and BDR activity (beyond quantity targets)

- Intent data, ICP data, and shared knowledge consistently in use

- Coordinated buyer journeys and pre/post-sales handoffs

- Conversion data and customer intelligence consistently fed and used

## Outcomes

- Repeatable: Same motions across teams producing consistent results

- Predictable: Known ramp time, accurate pipeline forecasting

- Scalable: Accurate forecasting and capacity planning with budget allocation to highest-performing channels

- Clear documentation of WHY targets were hit or missed

# Open Questions Requiring Resolution

The following questions need leadership alignment before full program execution:

- X-sell as distinct motion: Should cross-sell be a distinct motion with its own targets, ownership, and programmatic focus separate from CS upsell?

- Comp structure alignment: Does lifetime MRR payout dilute hunger for new wins? Is current comp complexity necessary or counterproductive?

- Technology/data as value-add: Where and how can we sell our technology and data assets as differentiated value-adds?

# Dependencies

## Technology & Business Systems

- Business Systems support for SFDC/Gong/marketing automation integrations

- Data Team capacity for data mart development supporting campaign and activity analytics

- Product/Technology alignment on portal and AI system capabilities for proposal automation

- Commission team assistance for comp tool implementation

## Cross-Functional Participation

- Sales team adoption of processes and consistent feedback on tools

- CX participation in win/loss program, case study development, and buyer journey mapping

- Strategic Insights engagement for data analysis, testing framework, and attribution modeling

- Marketing collaboration on ICP operationalization and content strategy

## External

- AUX continued advisory support through Q2

- Vendor responsiveness for marketing automation and Gong implementations

# Risks

## Capacity & Adoption

- Sales team growth uncertainty: Unclear 2026 headcount plans may strain enablement capacity or leave resources underutilized. Mitigation: Establish quarterly capacity review cadence with Sales Leadership.

- Tool adoption resistance: New tools require behavior change; without accountability mechanisms, adoption may lag. Mitigation: Identify internal champions, establish usage metrics, tie adoption to manager diagnostics.

- Cross-functional coordination failure: Without clear ownership of feedback loops and handoffs, silos persist. Mitigation: Establish named owners for each cross-team process with escalation paths.

## Data & Measurement

- Data quality gaps: Analytics and attribution require clean, consistent data entry. Mitigation: Implement data quality enforcement and regular audits in Q1.

- Content library staleness: Without ongoing refresh mechanisms, content loses relevance within 12 months. Mitigation: Establish ownership and update cadence for each content category.

## Strategic Alignment

- Comp structure misalignment: If compensation continues to reward behaviors counter to program goals, enablement efforts will underperform. Mitigation: Escalate comp structure questions for Q1 resolution.

- X-sell ambiguity: Without resolution on cross-sell ownership, gaps may persist between CS and Sales motions. Mitigation: Secure leadership decision by end of Q1.

# Version History

| Date | Version | Changes |
| --- | --- | --- |
| Dec 2025 | Draft v2 | Incorporated alignment notes from Programs 01/02 review; added missing elements, success criteria, open questions, and expanded dependencies/risks |