# 2026 PROGRAM PLAN

Program: Program 4: Optimized Foundations

Projects: Data Gov v1, Data Gov v2 Build, Data Mart and Catalog Build/Enablement, AI Assisted Reporting

Planning Period: January 1 – December 31, 2026

Version: 12/12 Draft

## Program Priorities in 2026

- Mature Data Governance Framework

- Enable Self-Service Analytics

- Improve Data Quality & Transparency

- Strengthen Culture & Adoption

## Q1:

Quarter Focus: Formally launch the Data Governance Program by initiating domain reviews using the initial set of Salesforce data quality reports. In parallel, we will expand data accessibility by continuing to build and enhance data marts within the Data Platform. To ensure consistency, control, and quality in key reporting, we will centralize report development within the Data Platform Operations team.

### Key Deliverables

| Q1 Deliverable | Owner | Supported By | Target Date |
| --- | --- | --- | --- |
| Communicate report builder structure change to employees and importance of business systems intake process and data platform documentation | Alex | Business Operations for Change Management, Additional Touchpoint comms and STACKWISE |  |
| Centralize Report team under Data Platform (Single resource in Q1/2 – Alex Titus). Build intake process and determine backlog and prioritization framework. | Thomas | Insights, Finance, Advisory Ops, Goy, Strategic Insights | 3/31/26 |
| Kick off Data Governance program with Domain Reviews using v1 Salesforce Reports - get teams used to the program and work out kinks in process and cadence | Moe | Sales, Advisory Ops, CX, Commissions, Business Operations | 2/15/26 |
| Build out Data Mart/Collections for data sets not yet accessible, in order of priority | Thomas/ Shivani | Data Engineering | Ongoing based on priority |
| Semantic Layer tool eval and initial integration build | Thomas/ Shivani | Data Engineering, Engineering | 3/31/26 |
| Complete Data Catalog and Semantic Layer KT and begin documentation | Thomas | Data Engineering, Strategic Insights, Product | 3/31/26 |
| Tally Reconciliation Functionality | Jade | Engineering, Shivani | 3/31/26 |

Key Metrics:

- Number of Domain Reviews Completed: Tracks cadence and adoption of governance reviews.

- Data Mart Coverage: Number of priority datasets made accessible via data marts.

- Report Builder Capacity: Prioritization backlog

- Reports in backlog vs built/published

- Policy Coverage: Percentage of Salesforce fields with governance rules applied.

- Issue Resolution Rate: Percentage of identified data issues corrected

- Logic and Semantics documented for Semantic Layer

## Q2:

Quarter Focus: Advance our data foundation by building the Data Catalog and Semantic Layer and completing discovery and preparation for the Data Governance Engine so development can begin in early Q3 once budget is approved. Product will focus on getting new system sources into the data platform.

### Key Deliverables

| Q2 Deliverable | Owner | Supported By | Target Date |
| --- | --- | --- | --- |
| Data Catalog and Semantic layer logic build | Thomas | Data Engineering, Engineering | 6/30/26 |
| Data Governance Engine discovery and pre work so we can begin build beginning of Q3 when budget is unlocked | Thomas | Partner, Data Assurance, Data Engineering | 6/30/26 |
| Discovery and backlog built for Data ingestion from tools rolled out in Q1: Marketing Automation, Gong Sales Comp Tool, Lumopath | Shivani | Data Engineering, Business Systems | 6/30/26 |

Key Metrics:

- Policy Compliance Rate: Percentage of domains adhering to governance policies.

- Number of metrics built into Semantic layer

- Number of Epics related to new system data ingestion

- Report backlog reduction with additional headcount

## Q3:

Quarter Focus: Advance governance maturity by building out v2 weighted and scored reports, snapshotting the data. Begin formally enabling AI with Data Platform.

### Key Deliverables

| Q3 Deliverable | Owner | Supported By | Target Date |
| --- | --- | --- | --- |
| Move Julie M to reporting team (Sales Comp tool implementation in Q1 is cause of delay move) | Thomas | Advisory Ops | 7/1/26 |
| Build out Data Governance Rules Engine and Scoring (all critical data in platform) and Begin snapshotting Data Quality Scoring for trend analysis | Thomas | Partner, Data Assurance | 9/30/26 |
| Test weighting and scoring reports | Thomas | Sales, Advisory Ops, CX, Commissions, Finance | 9/30/26 |
| Set up Visualization MCP to enable the use of Claude or other AI models in analytical insight exploration and visual report building. | Thomas | Data Engineering, AI | 9/30/26 |

Key Metrics:

- Number of data scores built out per source system

- Number of trend reports built for data quality

## Q4:

Quarter Focus: Broad availability of Data Governance scoring and reporting

### Key Deliverables

| Q4 Deliverable | Owner | Supported By | Target Date |
| --- | --- | --- | --- |
| Roll out v2 Data Governance Reports (with weighting and scoring) | Moe | Sales, Advisory Ops, CX, Commissions, Finance | 12/31/26 |
| Publish Data Policies with scoring and weighting methodology | Thomas | Business Operations | 12/31/26 |
| Build Data Quality trending reports using snapshot data including audit capabilities within the data quality scoring data | Thomas | Data Engineering, Analyst | 12/31/26 |

Key Metrics:

- Domain reviews done with new Data Governance scoring reports

- 5% improvement of data quality scores

## What Success Looks Like

By December 31, 2026, this program will have achieved:

- Baseline (starting point):

  - Salesforce Reports for Data Monitoring. Capture # of records delinquent on each policy 1/1/26

  - Number of Data Collections available for self-serve reporting. Capture on 1/1/26

  - Number of tables documented in Data Catalog. Capture on 1/1/26

- Targets (specific goals)

  - # of records delinquent on each policy should be 10% lower than the start of the year

  - Data Collections available for self-serve reporting backlog within 3 months of submission to Product backlog

  - Number of tables documented in Data Catalog and logic captured in Semantic Layer

- Impact (expected outcomes)

  - Trusted data for financial reporting and Client Portal use

  - Business reporting needs addressed within Analysts, not reliant on Data Engineering timeline and processes

- Decision criteria (how to evaluate success/pivot)

## Dependencies of Note

- The level of budget and resourcing determines how many reports can be produced and how much data quality can realistically improve.

- If the business lacks capacity to address issues surfaced in the reports, data quality will stagnate or decline.

- Funding for an external partner will determine when in the plan we can execute data governance across platform.

- Having a single Report Builder for the first two quarters will reduce the amount of reports that team cna produce for the business. Will rely on Strategic Insights to enforce prioritization.

## Risks of Note

List any risks that need to be mitigated in order to meet company & department goals:

- If program is not funded or teams cannot allocate resources, success criteria cannot be met