# 2026 PROGRAM PLAN

Program: Program 5: Alignment & Accountability

Projects: Regular re-prioritization & decision making in the open via the Gateway & UPSTACKer Experience, Connection, and Development (Q1-Q4 2026)

Planning Period: January 1 – December 31, 2026

Version: 251119 Draft

## Program Priorities in 2026

- Strengthening the foundation that underpins our sales and CX efforts

  - Transform decision-making and execution through a single prioritization framework, invest in consistent communication, align incentives and recognition, and foster connection & growth

- Note: Support required from the VP leadership group will focus on the dissemination and ongoing reinforcement of priority communications to their direct reports and teams. Additional support to include contributing ideas for communication pilot programs, such as Behind the Scenes and the “Inside UPSTACK” podcast.

## Q425/Q126:

Quarter Focus: Improve & Pilot - Evaluate and improve upon existing career progression frameworks while launching/piloting new recognition, communication, and ways of working experiences.

### Key Deliverables

| Q1 Deliverable | Owner | Supported By | Target Date |
| --- | --- | --- | --- |
| The Gateway ¦ Launch version 2.0 to evolve from reactive decision-making framework into proactive operating governance system | Cybil Nielsen | Biz Ops, VPs | 11/30/25 |
| The Gateway ¦ Test version 2.0 amongst VP and ELT groups to capture learnings and opportunities for improvement | Cybil Nielsen | Biz Ops, VPs | 3/31/26 |
| Update core messaging ¦ Finalize the ‘UPSTACK Story’ and messaging to be embedded in all communications and employee touchpoints | Alex/ Anjana | ELT, VPs | 12/31/25 |
| Draft 1 of 2026 Culture Calendar delivered; Q1deliverables executed | Alex Cole | Giang, Biz Ops | 1/31/26 |
| Update and disseminate “How We Work” documentation to all UPSTACKers | Alex Cole | Biz Ops, Advisory Ops, PO | 1/31/26 |
| UPSTACK Honors ¦ Corporate functions and Support team honorees nomination and selection for 2025 Honors Trip | Alex Cole | Advisory Ops (Kate Arel) | 1/31/26 |
| UPSTACK Honors ¦ Develop and distribute 2026 program announcement, including nomination criteria | Alex Cole | PO | 2/28/26 |
| Establish framework and execute one (1) UPSTACK Connects | Alex Cole | Giang | 2/28/26 |
| Establish framework for and launch one (1) “Behind the Scenes” pilot episode | Alex Cole | PO, Biz Ops, VPs | 3/31/26 |
| Establish framework for and pilot one (1) “Hindsight” Meeting | Alex Cole | Anjana, Biz Ops | 3/31/26 |

Key Metrics:

- ALL

  - Target: Deliverables completed by stated target date

- Establish framework and execute one (1) UPSTACK Connects

  - Program pulse survey results:

    - “I feel more connected to colleagues outside my immediate team.”

      - Target: Establish baseline; ≥70% “agree/strongly agree” (on scale of 1-5)

    - Pulse item: “I gained a better understanding of how different parts of UPSTACK work and how our roles interconnect.”

      - Target: Baseline established in Q1; improvement MoM across cohorts

- Establish framework for and launch one (1) “Behind the Scenes” pilot episode

  - Live attendance rate + recording views within 7 days

    - Target: Baseline in Q1; consistent MoM growth in either live or async participation

  - Viewer sentiment

    - Target:

      - 30+ NPS (“I would recommend Behind the Scenes to a colleague”)

      - Qualitative sentiment (≥50% positive/neutral)

- Establish framework for and pilot one (1) “Hindsight” Meeting

  - Program pulse survey results:

    - “It feels safe to discuss mistakes or unsuccessful outcomes at UPSTACK.”

      - Target: Establish baseline in Q1; aim for +0.2–0.3 improvement in Q2 (on scale of 1-5).

  - Number of teams/projects submitting stories or learnings for Hindsight sessions

    - Target: Baseline participation rate in pilot; aim for growth by Q2.

  - % of shared learnings that lead to follow-up actions, adjustments, shared best practices, or documentation

    - Target: Establish baseline; ≥50% conversion into some form of action.

  - Identify at least three (3) “Culture Champions” who can provide influence and help drive our culture agenda

## Q2:

Quarter Focus: Pilot & Scale - Refine connection initiatives and roll-out additional employee experience programming (in-person & virtual opportunities) to strengthen engagement and connection to the UPSTACK Story

### Key Deliverables

| Q2 Deliverable | Owner | Supported By | Target Date |
| --- | --- | --- | --- |
| Establish & rollout formal recognition program—“Spotlight”—with criteria and nomination process (designed to reinforce One UPSTACK and How We Work) | Alex | Giang, PO | 5/31/26 |
| The Gateway ¦ Update system to reflect key learnings captured during Q1 test phase | Cybil Nielsen | Biz Ops, VPs | 6/30/26 |
| Plan and execute up to two (2) UPSTACK Huddles (e.g., regional, cross-team or cross-functional gatherings) | Alex | Giang, Kate Arel, PO | 6/30/26 |
| Establish v1 of Employer Branding and Value Proposition (EVP) | Alex | Anjana, PO, ELT, VPs | 6/30/26 |
| Review outcomes of 1H26 pilot initiatives and provide go-forward recommendation | Alex | Giang, PO, Biz Ops, VPs | 6/30/26 |

Key Metrics:

1.2. Establish & Roll-out Formal Recognition Program (One UPSTACK / How We Work)

- Recognition criteria finalized and communicated

  - Target: 100% by launch date

- % of UPSTACKers participating (nominating or being nominated) monthly

  - Target: Establish baseline participation rate in Q2; trend up by Q4

- % of recognition stories explicitly tied to desired behaviors (e.g., cross-functional collaboration, tech adoption, insights driven)

  - Target: Establish baseline; aim for ≥70% by Q4

4. Plan and execute up to two (2) UPSTACK Huddles

- Attendance rate

  - Target: ≥80% of invitees

- Program pulse survey results

  - “The Huddle increased my understanding of current company priorities and how they relate to my work.”

    - Target: Establish baseline; aim for ≥4.1 average (UPSTACK’s internal “very strong” signal range) by Q3.

  - “The information shared in Huddles helps me work more effectively or make better decisions.”

    - Target: Baseline established in Q2; aim for ≥70% agree/strongly agree by Q3.

- Post-event survey participation

  - Target: ≥70% response rate

- Event NPS

  - Target: 30+

6. Refreshed Employer Brand and EVP

- EVP messaging finalized and approved

  - Target: 100%

- Updated branding assets deployed

  - Target: across 100% of relevant channels, such as SharePoint, careers webpage and LinkedIn

## Q3:

Quarter Focus: Pilot & Scale – Test new onboarding and annual planning experiences; assess impact of/ response to connection, communication and experience initiatives and activities from first half of the year; revise and tweak as needed, scale what works to maximize impact

### Key Deliverables

| Q3 Deliverable | Owner | Supported By | Target Date |
| --- | --- | --- | --- |
| Develop and launch pilot episode of the “Inside UPSTACK” Podcast | Alex | ELT, VP leadership, Biz Ops | 9/30/26 |
| Develop and launch pilot of “Intro Days” for TBD New Hire cohort in HQ1 & HQ2 (TBC) | Alex/ Giang | PO, VPs, ELT | 9/30/26 |
| Develop and launch inaugural “Strategy Days” event (TBC) | Alex | Biz Ops, ELT, VPs | 9/30/26 |

Key Metrics:

- 2026 UPSTACK Experience Survey

  - Increase survey score for “I feel connected to others at UPSTACK.”

    - Target: +0.20 points vs ‘25 score

  - Increase survey score for “There is transparency in UPSTACK’s actions and communications.”

    - Target: +0.30 points vs ‘25 score

- Develop and launch pilot episode of the “Inside UPSTACK” Podcast

  - % of employees who click/play within the first 48 hours

    - Target: Establish baseline for “open/play rate”

  - Listener sentiment

    - Target:

      - 30+ NPS (“I would recommend the podcast to a colleague”)

      - Qualitative sentiment (≥50% positive/neutral)

- Strategy Days Pilot

- New format and agenda confirmed and executed

- Improved stakeholder alignment

  - Target (lagging): Fewer projects marked Yellow or Red compared to 2026

- Program pulse survey results:

  - “Strategy Days strengthened alignment and collaboration across leadership levels and functions.”

    - Target: Baseline in Q3; improvement target of +0.2–0.3 at next Strategy Days

- Pilot Intro Days for New Hires

- Cohort identified and invited

- Sessions scheduled and run

- Attendance rate

  - Target: ≥80% of invitees

- % of new hires who report having the context, resources, and relationships needed to be successful

(e.g., “I felt set up for success after Intro Days.”)

- Target: Establish baseline in Q3; track improvements per cohort QoQ

  - Measured at 45- or 60-days post-onboarding

Q4:

Quarter Focus: Analyze & Sustain - Conduct a year-in-review of initiatives; conduct litmus test of messaging and storytelling impact across the organization; begin preparation for next-gen culture initiatives starting in 2027

### Key Deliverables

| Q4 Deliverable | Owner | Supported By | Target Date |
| --- | --- | --- | --- |
| Data insights of UPSTACK storytelling and messaging efficacy, collected and analyzed | Alex | PO, VPs | 11/30/26 |
| Draft plan for applying for Great Place to Work Certification in 2027 | Alex | PO, ELT, VPs | 11/30/26 |
| Plan and execute a minimum of one (1) UPSTACK Huddles (e.g., regional meetings/ cross-team or cross-functional gatherings) | Alex | Giang, Kate Arel, PO | 12/31/26 |
| Draft brief and source proposals for UPSTACK Values Refresh Project | Alex | Anjana, ELT, VPs | 12/31/26 |

Key Metrics:

- Data Insights on Storytelling & Messaging Efficacy

  - Data sources identified and collected

  - Engagement metrics tracked (e.g., views, shares, feedback)

  - Analysis completed and key themes summarized

  - Insights shared with relevant teams

- Draft plan for applying for Great Place to Work Certification in 2027

  - Evaluate pulse, Employee NPS, and Employee Experience survey results to gauge readiness for Great Place to Work Certification

  - If ready, establish GPTW application timeline, including key milestones, responsible parties, and dependences

  - GPTW application submitted by Feb 5, 2027, deadline

- Plan & Execute at least 1 UPSTACK Huddle (Same as earlier, but repeated for clarity)

  - Attendance rate

    - Target: ≥80% of invitees

  - Program pulse survey results

    - “The Huddle increased my understanding of current company priorities and how they relate to my work.”

      - Target: ≥4.1 average (UPSTACK’s internal “very strong” signal range) by Q3.

    - “The information shared in Huddles helps me work more effectively or make better decisions.”

    - Target: ≥70% agree/strongly agree by Q3.

  - Post-event survey participation

    - Target: ≥70% response rate

  - Event NPS

    - Target: 30+

- Draft brief and source Proposals for UPSTACK Values Refresh Project

  - Stakeholder input gathered

  - Third party prospect list drafted

  - Third party partner identified

  - Project plan for Q1 (or 1H) 2027 drafted

## What Success Looks Like

By December 31, 2026, this program will have achieved:

- 100% of incremental program or project requests evaluated and prioritized via The Gateway

- 95% of UPSTACKers being able to communicate the UPSTACK Story and messaging (the why behind what we are doing)

- Experience Survey scores for “Connection” and “Transparency” at our above survey average

- Increased accountability from individuals and teams across the organization demonstrated by changes in behavior and actions

## Dependencies of Note

List any critical dependencies you have on other teams in order to meet company & department goals:

- 2025 Honors Trip & UPSTACK Huddle meetings (in-person)

  - Event production support from Kate Arel, Advisory Ops, where needed

- VP leadership group

  - Support required from the VPs will primarily focus on the dissemination and ongoing reinforcement of priority communications to their direct reports and teams. Additional support to include contributing ideas for communication pilot programs, such as Behind the Scenes and the “Inside UPSTACK” podcast.

## Risks of Note

List any risks that need to be mitigated in order to meet company & department goals:

- Performance Risk: Increased disconnection driven by lack of consistent communication and context sharing may cause us to miss company objectives and delay our ability to scale

- Leadership Credibility Gap: Continued senior leadership alignment issues will cascade down, creating execution inefficiencies and talent retention risks

- Cultural Fragmentation: Remote-first operations can lead to deepening silos that may limit collaboration plus burning time and resources on how to do the work instead of doing the work