2026 PROGRAM PLAN

Program 03: Standardized, Tech-Enabled Experience

Projects: Establish CX Quality Standards, Targets & Measurement; Tech Enablement Roll-out

Planning Period: January 1 – December 31, 2026

Version: December 2025 Draft

## Program Priorities in 2026

- Deploy Lumopath across all CX functions with role-specific dashboards and management workflows

- Establish measurable quality standards (engagement, health, renewal, CSAT) with tiered targets

- Standardize customer-facing artifacts and CX playbooks into integrated, searchable systems

- Build reusable change management methodology for technology and process embedment

- Establish insights-to-action mechanism linking analysis to prioritized improvement initiatives

- Define AI augmentation ownership framework for agents, knowledge bases, and workflows

## Q1: Foundation & Discovery

Establish baseline infrastructure: complete Lumopath rollout, catalog existing artifacts and processes, define quality metrics and measurement methodology.

Key Deliverables

| Deliverable | Owner | Supported By | Target Date |
| --- | --- | --- | --- |
| Lumopath rollout complete for all CX staff with role-specific dashboards deployed | CX Directors | Product, Advisory Ops, BizOps | Mar 31 |
| Artifact inventory completed with metadata (owner, purpose, maintenance time) | Amy/Tim Fuller | CX Directors, Product | Mar 31 |
| Playbook V1.0 gap analysis completed across all CX groups | CX Directors | BizOps | Mar 31 |
| Quality metric definitions finalized (engagement, health, renewal, CSAT) | Kurt Walk | CX Directors, Finance | Mar 31 |
| Cost-to-support methodology selected (Lumopath vs Tableau) | Kurt Walk/Aditi | Finance, Product | Mar 31 |
| Portal training and $0 Assets migration completed | Kyle Radzinski | Product, Client Services | Mar 31 |
| Change management methodology framework drafted | Kurt Walk | BizOps | Mar 31 |

Key Metrics: 100% CX staff Lumopath access; artifact inventory completeness; metric definitions signed off

## Q2: Operationalization

Transition from deployment to active usage: embed Lumopath in daily workflows, prioritize artifacts for transformation, begin playbook updates, launch automated metrics.

Key Deliverables

| Deliverable | Owner | Supported By | Target Date |
| --- | --- | --- | --- |
| Lumopath fully operational with triggers and 1:1 workflows established | CX Directors | Product | Jun 30 |
| Artifact prioritization completed with transformation roadmap; Q2 transformations delivered | Amy/Tim Fuller | CX Directors, Product | Jun 30 |
| Playbook V2.0 draft content validated with leadership | CX Directors | BizOps, Advisory Ops | Jun 30 |
| Automated cost-to-support metric launched for executive review | Kurt Walk/Aditi | Finance, Product | Jun 30 |
| Customer Engagement and Health Scoring automated in Lumopath | Eric Nygard/Kurt Walk | Product | Jun 30 |
| Portal integration with SD update links operational; 45 activations (Apr-Jun) | Kyle Radzinski | Product, CSMs/SDMs/PTMs | Jun 30 |
| Cross-team prioritization process and insights-to-action mechanism piloted | Kurt Walk | FP&A, CX Directors | Jun 30 |

Key Metrics: Lumopath daily active usage; cost-to-support automation (50% effort reduction); Portal activations (15/month)

## Q3: Refinement & Publication

Publish standardized playbooks, operationalize quality standards, assess AI augmentation opportunities, and expand Portal use cases.

Key Deliverables

| Deliverable | Owner | Supported By | Target Date |
| --- | --- | --- | --- |
| CX Playbooks V2.0 published with training delivered and review cadence established | CX Directors | BizOps | Sep 30 |
| Q3 artifact transformations delivered; governance for non-integrable artifacts established | Amy/Tim Fuller | Product, BizOps | Sep 30 |
| Renewal Management and CSAT scoring operational; all four metrics in real-time dashboards | Kyle Radzinski/Erica/Jeff | Product, Finance | Sep 30 |
| Tiered quality targets validated and communicated | Kurt Walk | CX Directors | Sep 30 |
| AI augmentation assessment completed with ownership framework documented | TBD (AI Lead) | CX Directors, Product | Sep 30 |
| Portal external inventory sources onboarded; 90 cumulative activations | Kyle Radzinski | Product | Sep 30 |
| Change management methodology finalized | Kurt Walk | BizOps | Sep 30 |

Key Metrics: Playbook adoption rate; quality metric dashboard utilization; CSAT response rate; AI opportunities identified

## Q4: Optimization & Planning

Measure full-year impact, refine based on feedback, complete remaining transformations, and plan 2027 enhancements.

Key Deliverables

| Deliverable | Owner | Supported By | Target Date |
| --- | --- | --- | --- |
| Remaining artifact transformations completed; AI-enabled maintenance pilots launched | Amy/Tim Fuller | Product, AI Lead | Dec 15 |
| Full-year quality metric analysis with correlation to retention outcomes | Kurt Walk | Finance, BizOps | Dec 15 |
| Cost-to-support trend analysis and executive insights delivered | Aditi | Finance, CX Directors | Dec 15 |
| Playbook and insights-to-action effectiveness reviews completed | CX Directors/Kurt Walk | BizOps, FP&A | Dec 15 |
| 120 cumulative Portal activations achieved; 2027 expansion plan drafted | Kyle Radzinski | Product | Dec 31 |
| 2027 Program 03 roadmap drafted with priorities | Kurt Walk | CX Directors, BizOps | Dec 31 |

Key Metrics: Quality metric improvement YoY; artifact transformation completion; Portal adoption (120 total); cost-to-support efficiency gains

## What Success Looks Like

By December 31, 2026, this program will have achieved:

- Lumopath embedded in daily CX operations with role-specific dashboards driving proactive customer management

- Real-time visibility into all four quality metrics with demonstrated correlation to retention outcomes

- 50%+ reduction in manual effort for cost-to-support measurement with automated trend analysis

- High-priority customer-facing artifacts integrated into standardized UPSTACK tools

- CX Playbooks V2.0 serving as definitive operational reference with active governance

- 120+ Portal activations with embedded service delivery workflows

- Reusable change management methodology enabling technology embedment without major disruption

- Clear AI ownership framework with documented assessment of automation opportunities

## Dependencies of Note

- Product team capacity for Lumopath dashboard development and Portal enhancements

- Finance team availability for cost-to-support validation and Tableau integration

- Business Operations support for SharePoint playbook repository and change management documentation

- Program 04 data domain ownership definitions (required for semantic consistency, especially for AI)

- Program 02 sales enablement process documentation (for integration into artifact catalogue)

- Advisory Operations alignment on cross-functional workflow standards

## Risks of Note

- Lumopath adoption lag if dashboards don't demonstrate immediate value; mitigate via role-specific validation with directors before broad rollout

- Artifact transformation scope exceeds capacity; mitigate via strict prioritization based on time-savings and customer impact

- Quality metrics lack automation paths; mitigate via early Lumopath capability assessment and manual-plus-automation hybrid fallback

- Playbook updates stall without cross-functional engagement; mitigate via structured workshops with clear ownership

- AI ownership undefined; mitigate via early framework definition before broad assessment

- Change management stays theoretical; mitigate by embedding methodology in Q2 Lumopath operationalization as proof case