# 2026 PROGRAM PLAN

Program: Intelligent Organic Growth

Projects: Fuel growth with accessible sales, customer, and market intelligence & Test and align to optimized GTM strategy, sales approach, and playbook creation

Planning Period: January 1 – December 31, 2026

Version: 10/29/2025 Draft

## Program Priorities in 2026

- 20% of new revenue growth net new logos

- 15% Direct sales revenue growth

- 3x pipeline coverage to MRR revenue targets

- Expedite ramp schedule of new sales headcount

- Ensure a strong alignment between sales objectives and our evolving business strategy.

- Continued focus on building consistent sales processes and enablement tools supporting growth.

- Continue to deepen cross functional alignment between sellers, team resources and departments (mainly CSM, client services) to boost cross sell velocity

- Monitor utilization and adoption of technology/tools investments for the team

- BDR organization over attainment to meetings target monthly

- Create industry centric playbooks comprised of top solution targets and complimentary product sets and packages

- Maximize CX practice investment, 33%+ CX MRR booked vs 2025

## Q1:

Quarter Focus: Finalizing outstanding tool selections. Conversion from MRC forecasting to MRR. Inspection of ramping sellers and BDRs performance. Beat 2024 Q1 MRR by 15%.

### Key Deliverables

| Q1 Deliverable | Owner | Supported By | Target Date |
| --- | --- | --- | --- |
| Commissioning tooling - Have a tool identified and signed by 12-31-25 with a goal to have fully implemented in Q2 | Kelley Moore | Charlie Day Product Team Commissions |  |
| Forecasting and Metrics - Create and iterate of forecast reporting including accuracy, conversion rates and other metrics | Kelley Moore | Charlie Day |  |
| Finalize complimentary product focus and industry technology solutions | Charlie | Dan Corning and Paul Vuoso | — |
| 90-day ramp plan reviews | Direct Sales Leader | Charlie | — |
| Activity tracking and productivity metrics framework – define LTV/CAC tie-ins | Ops | Sales Leadership | — |
| Unit economics definition and on-demand reporting framework | Ops | Finance, Sales Leadership | — |
| Data accuracy standards and tool adoption training/monitoring program | Ops | Sales Leadership, IT | — |
| Decision criteria framework: “if we find x in testing, we will do y” action plans | TBD | Sales Leadership, Ops | — |
| Determine X-sell motion: distinct targets and ownership vs. CS upsell | Charlie | CS Leadership | — |

Key Metrics: 3x MRR pipeline coverage to Q2 revenue target. Final MRR performance.

## Q2:

Quarter Focus: Getting new sellers on the board with mature opportunities and even some new wins. Using new pipeline reporting capabilities for trend analysis. Refinement of messaging and outreach tailored by industry.

### Key Deliverables

| Q2 Deliverable | Owner | Supported By | Target Date |
| --- | --- | --- | --- |
| Top industry playbook creation | TBD | Ops, Sales, SMEs | — |
| Inspection of BDR alignment to sellers vs specialization | Charlie | Ops, BDR leaders, Sales leaders | — |
| Inspect CX pipeline generation, compare YoY | Charlie | Ops, Mike Leonardi |  |
| Insight-to-action feedback mechanisms operational | Ops | Sales Leadership | — |
| BDR/Seller activity prioritization framework live (data-driven vs. qty targets) | Charlie | Ops, BDR Leaders | — |
| Intent data, ICP data, shared knowledge integrated and in consistent use | Ops | Sales, Marketing | — |
| Experimentation/testing cadence and framework established | TBD | Ops, Sales Leadership | — |
| Sales enablement training/collateral/data system consistently fed and used | TBD | Sales Enablement, Ops | — |

Key Metrics: Beat 2025 Q2 MRR by 15%. 4x Pipeline to Q3 MRR target. 75% of reps meet the reduced off-ramp quota target.

## Q3:

Quarter Focus: All hands-on deck, all new sellers off ramp.

### Key Deliverables

| Q3 Deliverable | Owner | Supported By | Target Date |
| --- | --- | --- | --- |
| ROI Review of Events - Review all event tracking to determine success and planning for next year | Kelley Moore | Direct sales leadership, SMEs | — |
| Full realization of AUX deliverables from marketing | Charlie | Kelley | — |
| [Specific deliverable/result by end of Q3] | [Name] | [Department/Team] | — |
| Conversion analytics and win/loss intelligence operational | Ops | Sales Leadership | — |
| Diagnostic infrastructure for managers – insights on team performance | Ops | Sales Leadership | — |
| Coordinated buyer journeys and pre/post-sales handoffs documented and trained | Charlie | CS Leadership, Sales | — |
| Targeting and engagement aligned to messaging hooks known to work | TBD | Sales Enablement, Marketing | — |
| Structured log of insights-driven tests, decisions, actions, and results maintained | Ops | Sales Leadership | — |

Key Metrics: % off ramp sellers to plan. Beat 2025 Q3 by 15%. 4x Pipeline coverage for Q4 target.

## Q4:

Quarter Focus: Hitting our stride, fully ramped team, tools and reporting in place. We should have a strong gauge on whether we are in a position to continue expanding the sales organization's headcount.

### Key Deliverables

| Q4 Deliverable | Owner | Supported By | Target Date |
| --- | --- | --- | --- |
| TBD | [Name] | [Department/Team] | — |
| Analytics validated: input produces output at activity level | Ops | Sales Leadership | — |
| Repeatable motions confirmed – same approach across teams | Charlie | Sales Leadership | — |
| Predictable results verified – known ramp time, accurate forecasting | Ops | Sales Leadership, Finance | — |
| Scalable model validated – capacity planning, budget allocation to highest-performing channels/activities | Ops | Finance, Sales Leadership | — |
| EOY assessment: replicate what works, diagnose gaps, distribute findings with clear ownership | Charlie | Ops, Sales Leadership | — |

Key Metrics: 100%+ to annual MRR target, sales team contribution %, pipeline coverage going into 2027.

## What Success Looks Like

By December 31, 2026, this program will have achieved:

• 15% organic revenue growth

- 20% of new revenue from new logos and add on orders to those logos

- 33% increase in CX MRR

- 80% of sales team above quota

- Overperformance to BDR meetings target

- Consistent 3x pipeline coverage

- Minimal attrition for direct sellers, leadership, and SMEs

- Increased output of repeatable processes aligned to sales execution for success that can scale with future growth

## Dependencies of Note

List any critical dependencies you have on other teams in order to meet company & department goals:

- Tool selection and deployment = Ops and product

- Ops getting enhanced reporting capabilities in place

- AUX deliverables on marketing. We are being asked to begin 2026 with highly increased headcount, need to accelerate the pipeline with no marketing organization in place.

- Performance of new sales team beginning in 2nd half of the year

## Risks of Note

List any risks that need to be mitigated to meet company & department goals:

Need to continue top-down push to make UPSTACK a revenue focused organization. Update bonus plans for eligible departments to be aligned to our topline revenue performance and not EBITDA. Enhance communications about our performance to revenue targets outside of the sales organization.